## HAZOP actions
action | node | finding | owner | due | status
H-7-14 | Node 2 - Accumulator | Confirm PSV-7301 relief load against re-rated envelope | S. Nair | 2026-06-30 | CLOSED
H-7-18 | Node 2 - Accumulator | Replace PSV-7302 and close NCR-2026-0412 before next startup | A. Menon | 2026-10-15 | OPEN
H-7-22 | Node 3 - Overhead condenser | Carry out first thickness survey of E-7204 - no baseline exists | M. Rao | 2026-11-30 | OPEN
H-7-27 | Node 1 - Tower | Verify T-7001 reflux line material against chloride SCC review | A. Menon | 2027-01-31 | OPEN