## Slide 1: Pre-Shutdown Review — CDU-II
Inspection Dept · 13-Sep-2026

## Slide 2: TK-4102 — Open Items
Shell thickness 11.2 mm vs nominal 12.0 mm
  PSV-2041 set at 12.5 barg — SOP-114 requires 14.0 barg
  Quarterly UT monitoring mandated until 31-Mar-2027
  MOC-2026-0231 conditional approval in force

## Slide 3: Shutdown Scope
Bench test and reset all relief valves in CDU-II
  Weld overlay at course-1 if thickness < 10.8 mm
  Replace nozzle N-3 reinforcement pad
  Estimated duration: 9 days